## Sheet1
Date | Task | Status
18-10-2025 | Setup environment, XAMPP/WAMP, project folder structure | Done
19-10-2025 | Create MySQL database and tables, test connection, basic Bootstrap template | Done
20-10-2025 | Company registration and admin signup page | Pending
20-10-2025 | Employee login page and session setup | Pending
21-10-2025 | Role-based access control, test multi-company login | Pending
22-10-2025 | Employee attendance page (Clock-in/Clock-out) | Pending
22-10-2025 | Admin attendance view filtered by company | Pending
23-10-2025 | Dashboard summary of attendance | Pending
24-10-2025 | Leave application form for employees | Pending
24-10-2025 | Admin leave approval/rejection | Pending
25-10-2025 | Leave status update and dashboard integration | Pending
26-10-2025 | Admin announcements posting page | Pending
26-10-2025 | Employee announcement view | Pending
27-10-2025 | Document upload page | Pending
27-10-2025 | Document download and access restriction | Pending
28-10-2025 | Integrate document module with dashboard | Pending
29-10-2025 | Admin dashboard: attendance stats, pending leaves, documents | Pending
30-10-2025 | Employee dashboard: personal attendance, leave status, announcements | Pending
31-10-2025 | UI finalization and responsive design | Pending
01-11-2025 | Test all modules with multiple companies, fix bugs | Pending
02-11-2025 | Final bug fixes and integration testing | Pending
03-11-2025 | Deploy to cloud hosting | Pending
04-11-2025 | Test live deployment, backup database and files | Pending
05-11-2025 | Prepare report, screenshots, demo script for exam | Pending